## Sheet1
Task ID	Feature	Description	Code – Estimate (hours)	Layout – Estimate (hours)	Test – Estimate (hours)	Status
Kyler_001	Load List Songs	Load all audio file from sd card	6	2	1	In progress
Kyler_002	Load detail	Load the song detail	3	3	1	to do
Kyler_003	Play button	Play the music from that file	2	1	1	to do
Kyler_004	Stop button	Stop the music	2	1	1	to do
Kyler_005	Favorite button	Mark the song to the favorite list	2	1	1	to do
Kyler_006	Forward button	Forward the music 5 seconds	2	1	1	to do
Kyler_007	Back button	Back the music 5 seconds	2	1	1	to do
Kyler_008	Next button	Play the next song	2	2	1	to do
Kyler_009	Previous button	Play the previous song	2	2	1	to do
Kyler_010	Play progress bar	Forward or back the music by progress bar	3	2	1	to do
Kyler_011	Filter	Filter the song by artist, author, album if the audio file has that information	7	3	1	to do
Kyler_012	Timer	Schedule for the time stops music	2	3	1	to do
Kyler_013	Favorite Songs	Save the list of songs that favorite	5	5	1	to do
		Total	40	27	13
		Summary of times	80